## Summary-GroupIterationProgress
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks
0 | 09/06-09/20 | Learing git Git branching strategy - Git Flow Functional requirements Setup app foundation Risk identification Setup PivotalTracker Establish tech stacks Code style research Design Technology stacks for project |  | - Assigning documentation tasks | - Documentation responsibility - Team member awareness to the group's document | [5 empty] | 81.95 | 64.45 | 17.5 | 0 | 15.5 | 18.95 | 4 | 12.45 | 0.3 | 7
1 | 09/20-10/22 | Implementation Google API Login Setup all Firebase instances Requirement Analysis for Iteration 1 Scrum meeting - Weekly meeting Assign Tasks and Scrum Pokers Setup and config build tools and android distribution Setup appcenter Update PivotalTracker to Iterations | - Team's member have too much learning curve. | - personal issues among members | - start implementation of essential features | 5 | 12 | 0 | 0 | 0 | 170.5 | 138.5 | 32 | 0 | 47 | 19 | 15 | 31.5 | 0 | 17
2 | 10/22 - 11/13 | Implement Backend Code (Creating chatroom, send a message) Implement and setup for notifcation features Update UI and Application icon Setup Unit test and UI tests platform Update meeting schedules | - Team's member have too much learning curve. - All tech stacks are too new for team members | - member's health (flu) | - complete some features - refactor existing code - add unit tests | 5 | 12 | 0 | 0 | 0 | 163 | 133 | 30 | 0 | 46.5 | 18 | 14 | 32.5 | 0 | 17
3 | 11/13 - 12/10 | Fully integrate backend-android Complete login features Complete logout features Complete send message to backend Complete notification Complete add new chatroom Complete View User's profile Add unit and UI tests | - Most tasks are behind the plan - Still a lot learning curve in team's member - Features delivery is not good as expected | - Most tasks are behind the plan | - deliver features - add ui tests - add more unit tests - automatic deployment | 15 | 0 | 0 | 0 | 0 | 288.5 | 241.5 | 47 | 0 | 67 | 14 | 21 | 73 | 29 | 17

## projectcontribution
You should clearly describe your contribution to the group project in each category. (This is not the final iteration contribution. It is the whole semester contribution)
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Wasupol Tungsakultong | - Plan overall contents - Write process model - Write related work - Write implement and deployment plan | - creating one story on Pivotaltracker | - Planing tech stacks and architecture to use in the project. - Add Design Pattern used - Add system architecture - Add detail implementation |  | - Plan overview of presentation - Outline presentation - Writing process model - Writing project timeline | - setup branches. - setup git structure. (Git flow) - setup branches rules'. - setup folder structure. |  | - set up automatic build tools (fastlane) - set up CI/CD (appcenter/circleci) | - Assigned roles and duties to team members - Assigned team plan and weekly meeting to the team
Jian Ma | - Set the tone for our product - Wrote the overall introduction - Wrote the competitive analysis |  | -Contributed features and design for our application |  | - Contributed overview of presentation - Writing overall introduction - Writing competitive analysis | - Contributed branches. - Contributed git structure. (Git flow) - setup files on git |  |  | - Had meetings with team member - Communicated daily by Slack
Peter Lake | - Wrote the quality assurance section | - Wrote several complete stories and contributed acceptance tests to others. | -Started class diagram for firebase implementation | -Summarized acceptance test results -Catalogued unit & UI tests | - Wrote QA slide and created a chart to depict gitflow. | -Updated login UI with logo | -Manual testing of app log in/log out -UI testing |  | -Meeting and communication via Slack -Contributed to risk management
Michael Ranasinghe |  | -Developed several user stories |  |  | - Contributed project management slide - Recorded video of querying users | -Contributed branch AddUserChatEmail - Contributed Google Login Branch - Contributed retrieving and creating chatrooms (however, this was not used as Po's implementation was better- ie much less code smells) |  |  | -Was accessible via Slack. I do best effort possible to be online slack ~16hr/day (just having it run in background with notifications on).

## Wasupol
Lead Roles: Project Leader, Configuration Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/06-09/13 | 8.5 | 5.5 | 3 | 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation |  | 2 |  |  |  | 2 | 0.5 | 1 | 1. Write 3 sections of SPPP 2. Participate in Iteration 0 presentation 3. Plan about process model, workflow to use in team project. | 1. communication is not clear. Task assignments is not clear. 2. very hard to setup meeting and communication because of mixture between online and in-person, also some team members live in difference time zone. | 1. Send task assignments to all members again. 2. Teach everyboard about git flow. | 1 - continue to define all requirements and start creating tasks 3 - setup android project in github. | 6
2 | 09/13-09/20 | 11 | 8 | 3 | 1 - define high level requirements, 1 - Design process model and timeline of the project 3 - Initialize android project on github 5 - make project plan, send reminders to team members 7 - prepare presentation |  | 3 |  | 1 |  | 2 |  | 2 | 1. Design project timeline for each iteration 2. Assign feature priorities 3. Clear up SPPP 4. Host meetings | 1. Not all members stay actively. | 1. Try to communicate more and direct | 1. Start working on implementation | 8
3 | 09/20-09/27 | 12 | 9 | 3 | 0 - Learning Pivot Tracker 1 - Planning tasks in Pivot Tracker 2 - Design Code and Document structure in github 3 - Add template code in github repository both backend and mobile code 5 - Reschedule weekly, start scrum meeting | 2 | 3 | 2 | 1 |  | 1 | [6 empty] | 10
4 | 09/27-10/04 | 12 | 9 | 3 | 1 - Update Readme.md 3 - update code structures 5 - Team weekly meeting, scrum meeting 6 - Setup gitflow branches |  | 2 |  | 2 |  | 3 | 2 | [5 empty] | 10
5 | 10/04 - 10/11 | 10 | 7 | 3 | 2 - Design folder structor of the project 3 - Setup template projects for both Android and Spring boot 3 - Setup Firebase project 6 - Configurate FCM message with the Android application |  | 2 | 3 |  |  |  | 2 |  | 1. Reviewing code 2. Setup Firebase instances 3. Fix defects of Google API login 4. Setup Firebase Firestore instance 5. Design data structure of Firebase Firestore. 6. Design chat mechanism for the application. | 1. team leader has personal issues so he can not 100% working on project. |  |  | 12
6 | 10/11 - 10/18 | 15 | 12 | 3 | 1, 5 - Iteration meeting for iteration 1 2 - Design overall software architecture to use in the project 3 - Implementation and setup Android and Backend project 5 - Configurate Pivotal Tracker like point and iteration 6 - setup automatic tools for building (fastlane), app center setup |  | 2 | 2 | 3 |  | 3 | 2 |  | 1. Reviewing code 2. Fix defects of Google API login 3. Implement fetch new messages listener 4. Implement the lifecycle of the application in each tab bar. 5. Setup distribution appCenter. |  |  |  | 15
7 | 10/18 - 10/25 | 13 | 13 | 0 | 1. Contribute in SDD, Data design, Design Patterns and System Architecture 3. Finalize code and application source code for Iteration 1, Fix defects in application source code 5. Plan for the next Iteration like tutorial and some demo for team member |  | 3 |  | 5 |  | 5 |  |  | 1. Finalize code and application source code for Iteration 1 2. Plan for the next Iteration like tutorial and some demo for team member 3. Contribute in SDD, Data design, Design Patterns and System Architecture 4. Fix defects in application source code |  |  | - start member trainning with Android development - explain what work has been done in the last interation - start restructure the code with backend - start integrate with backend | 18
8 | 10/25 - 11/1 | 11 | 8 | 3 | 3 - Start implement backend 5 - preparing demo, what was achieved in the last iteration in the term of implementation |  |  |  | 3 |  | 5 |  |  | 1. Design RestAPI endpoint and request that simply for client 2. setup code tutorial for team member 3. Start developing Backend with Java Spring boot |  |  |  | 15
9 | 11/1 - 11/8 | 8 | 6 | 2 | 1. Contribute in updating SDD, Data design, Design Pattern and System Architecture 3 Implement create a chatroom from Backend and save in firestore |  |  |  | 6 |  |  |  |  | 1. Contribute in SDD, Data Design and updated System Architecture 2. Fix defects in application 3. Start implementing code and core logics in backend 4. Setup FCM environment 5. Setup and add documents for setting up Android project for team member. | Lack of communication between team member |  |  | 15
10 | 11/8 - 11/15 | 13 | 11 | 2 | 1. Contribute in updating SDD, Data design, Design Pattern and System Architecture 3 Implement send a message from Backend and save in firestore 3 Implement send notification from backend to Firebase Cloud Message |  | 3 |  | 8 |  |  |  |  | 1. Finalize code and application deployment for Iteration 2 2. Plan for next iteration 3. Contribute in SDD, Data Design and updated System Architecture 4. Fix defects in application | Lack of communication between team member | Host 2 weekly meeting (shorter time like 30 mins) Always be active and response |  | 14
11 | 11/15 - 11/22 | 27 | 24 | 3 | 0. Has small tutorial sessions for programming 2. Design data structure to support notification feature 2. Improve existing design in messages and chat room for better query (better performance) 3. Start implementation of Android-Backend integration 4. Add more unit tests on backend side 5. Assign main responsiblity or owner of the tasks to team members 6. Setup automatical build tools with Fastlane | 2 |  | 4 | 8 | 4 | 3 | 3 |  | 1. Has fully running backend code on local machine 2. Add new branches in android-backend implementation 3. Has some unit tests on backend with TDD flow 4 Have clear owners of the tasks 5. Completely setup android build tool with fastlane | Lack of communication between team member | Host 2 weekly meeting (shorter time like 30 mins) Always be active and response |  | 13
12 | 11/22 - 11/29 | 30 | 27 | 3 | 0. Has small tutorial sessions for unit testing and ui testing 0. Learning Spring Boot Deployment with AWS 0. Learning Github Action to support build and test both platforms 2. Design data structure to save deviceToken effectively 2. Alter some data designs in messaging 3. Start implementation of updating user's profile picture. (with Firebase storage) 3. Fix issues on Android-Backend integration 4. Add more unit tests on backend and android side 6. Testing on deployment of backend (Spring boot java) to AWS EC2 6. Integration build tools with Github Actions | 5 |  | 3 | 8 | 6 |  | 5 |  | 1. Has fully running backend code on AWS 2. Finished android-backend integration for first release 3. Has some ui tests on Android with Esspreso 4 Have clear owners of the tasks 5. Completely setup android build tool with fastlane 6. Completely setup github actions for both project | Lack of communication between team member | Host 2 weekly meeting (shorter time like 30 mins) Always be active and response |  | 15
13 | 11/29 - 12/06 | 26 | 21 | 5 | 0. Has small tutorial sessions for unit testing 2. Design data structure to add friends feature 3. Improve existing logic in update user's profile to update all nodes with new user's image. 3. Start implementation of adding friend from user's list in the system 4. Add more unit tests on backend side 5. Assign main responsiblity or owner of the tasks to team members 6. Testing all envionments for building and distributing all apps | 3 |  | 3 | 3 | 4 | 3 | 5 |  | 1. Deliver new features (Add friends from backend) 2. Fix all known issues 3. Has some unit tests on backend |  |  |  | 24
14 | 12/06 - 12/10 | 34 | 29 | 5 | 2. Alter design data structure to collections in adding friend feature. 3. Start implementation of View Profile Page 3. Finalize the application and backend before final presentation 4. Add more unit tests on backend side 5. Assign main responsiblity or owner of the tasks to team members 5. Assign main responsiblity or roles in presentation and documents 6. Configurate the building tools to build only some events. |  |  | 3 | 14 | 4 | 4 | 4 |  | 1. Finally have full application with essential features 2. Add one activity diagram (login) 3. Add one sequence diagram (sending message) 4 Fully CI with Github Action (build, test, deploy) 5. Refactoring a lot of lines of code 6. Demo Video 7. Unit and UI tests in video 8. Contribute in all documents (SPPP, SDD, Code) 9. Contribute in presentation

## Peter
Lead Roles: QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/13-09/20 | 5.75 | 4.75 | 1 | 0 - Learning basic git and watching pivot tracker tutorials 1 - Researching QA requirements for SPPP 3 - Lab 1 git work 7 - Software liscense look ups | 3 | 0.5 |  | 1 |  |  |  | 0.25 | 1. Set up git, commit to team introduction. 2. Looked up liscensing for QA/testing software: Junit, Selenium and Appium are all open sourced | 1. Ended up using git GUI rather than the console so I still need to spend more time familarizing myself with git. 2. Unsure of role in iteration 0 presentation & SPPP beyond basic statements concerning the QA Plan | 1. Discuss presentation and SPPP responsibilities on 9/20 | 1. Complete separate git tutorials using only the console 2. Contribute to SPPP | 6
2 | 09/20-09/27 | 8 | 6 | 2 | 0 - Read about types of QA tests and testing methods 7 - Prepare presentation, made gitflow defect management and prioritization flow chart, contribute to SPPP | 2 | [6 empty] | 4 | 1. QA section of SPPP 2. QA slide for presentation | 1. I need to learn about testing requirements and designing tests 2. It is difficult to write the task associated with user stories without having an undertanding of how chat software works. | 1. Discuss requirement analysis with group and review class materials about requirement analysis. | 1. Complete Lab 2 work 2. Complete risk analysis survey | 12
3 | 09/28-10/4 | 5 | 5 | 0 | 0- Learning about Pivotaltracker, EBC & UML class diagrams 1- Wrote user stories for lab 2 and class diagram | 3 | 2 | [6 empty] | 1. User stories in Pivotaltracker |  |  |  | 19
4 | 10/5 - 10/11 | 6.5 | 3.5 | 3 | 0- Read about using firebase to store user information 1- Additional user story creation and refinement 6- Installed and configured Android studio & IntelliJ | 1 | 2 |  |  |  |  | 0.5 |  | 1. User stories in Pivotaltracker | 1. Unsure of intended functionality of user feeds while writing user storied; we'll need to discuss this in a future iteration. 2. I'm worried about technical debt from me: firebase and regression testing. |  |  | 25
5 | 10/12 - 10/18 | 6.5 | 5.5 | 1 | 0- Continued to learn about firebase and started familiarizing myself with the android framework. Android studio tutorials 2- Started class diagram for backend firebase implementation since it will be needed to support initial user stories 7- Added information to risk management spreadsheet | 4 |  | 1 |  |  |  |  | 0.5 | 1. Risk management document 2. Backend class diagram |  |  |  | 30
6 | 10/19 - 10/25 | 5 | 4 | 1 | 0 - Android studio tutorials and starter project practise. Kotlin practise. Reading course notes related to testing. | 4 | [8 empty] | 1. Not compenent enough with android to start user stories from scratch. 2. There hasn't been time to begin any testing beyond manual testing by Po and Michael |  | 1. Review unit test content 2. Become familiar with current production code | 40
7 | 10/26 - 11/1 | 4 | 2 | 2 | 6- Spent time attempting to configure Android Studio in order to perform manual testing of login | [6 empty] | 2 | [5 empty] | 45
8 | 11/2 - 11/8 | 6 | 5 | 1 | 0 - Continued Android tutorials and worked with a starter project 6 - Resolved issues with Android/Firebase configuration that prevented google authentication | 4 | [5 empty] | 1 | [5 empty] | 50
9 | 11/9 - 11/15 | 15 | 13 | 2 | 0 - Researching techniques and configurations for unit & UI testing 3 - Created logo and added it to app login page 4 - Worked on unit test for google login, wrote up test reports for login page acceptance tests. 6 - Configured appium | 4 |  |  | 2 | 4 |  | 3 |  | 1. Software testing document 2. Unit tests for Lab 3 3. Updated log in UI with logo, marked user story as complete. | 1. Had difficulty configuring Appium/implementing UI test. 2. Unsure of how to write unit tests for the types of methods in the log in UI. Some of the assert statements that seem appropiate are failing to import. |  |  | 55
10 | 11/16 - 11/22 | 7 | 6 | 1 | 0 - Completed Kotlin fundamentals tutorial 7 - Met with professor to discuss testing options & suitability with existing code. | 5 | [6 empty] | 1 |  | 1. Determined that my knowledge of Kotlin & Android was insufficient to attempt unit testing so I focussed on building my competency in both |  |  | 61
11 | 11/23 - 11/29 | 7 | 6 | 1 | 0 - Android framework tutorials. Began reading about Mockito for unit testing and Espresso for UI testing (recommended by professor). | 6 | [11 empty] | 67
12 | 11/30 -12/6 | 4.5 | 3.5 | 1 | 4 - Implemented UI tests for login/logout activity 6 - Configured project to include necessary dependencies for Espresso |  |  |  |  | 3 |  | 0.5 |  | 1. UI tests |  |  |  | 70.5
13 | 12/7 - 12/13 | 7 | 6 | 1 | 4- Implemented UI tests for navigation to messages, friends list, friend search etc. Manual acceptance tests for new features 7 - Worked on documentation and presentation |  |  |  |  | 4 |  |  | 2 | 1. UI Tests 2. Manual Acceptance Tests 3. Updated Testing Document 4. Presentation prep. | 1. Metric generation & code coverage reports |  |  | 78

## Michael
Lead Roles: Implementation Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/06-09/13 | 2 | 1 | 1 | 0 - learn git, read several tutorials 5 - team meeting | 1 | [7 empty] | 0. Set up git, commit a test message on git 5. Participate in Iteration 0 presentation | 0. Not to familiar with GitFlow | 0. Researching into GitFlow | 0 -learn GitFlow 1 - continue to define requirements | 3
2 | 09/13-09/20 | 3.5 | 2.5 | 1 | 0 - Learned GitFlow 1 - define high level requirements and prepare presentation 5- team meeting | 1.5 | 1 | [6 empty] | 0. Learned GitFlow 1. Write 3 sections of SPPP 3. Configuration list Powerpoint | 0. Need to start ramping up learning out to work with Kotlin and Firebase |  | 0 -learn Kotlin 0 - learn to work with FireBase? | 2020-10-12
3 | 09/27-10/04 | 8 | 5 | 3 | 0- Kotlin Bootcamp Learning 5- team meeting | 5 | [10 empty] | First Task from pivotal tracker: Google Login | 10
4 | 10/5-10/12 | 10 | 9 | 1 | 0 - video tutorials to implement google log in 3 - Implementation of Google Log In API | 5.5 |  |  | 3.5 |  |  |  |  | 0. Reading Kotlin manuals/ Watching Videos on Implementing Android with Firebase 3. Implementation of Google Log In API |  |  | 3. Add in Facebook API Login; ensure user information is recorded within Firebase | 6-10hrs
5 | 10/12-10/19 | 9 | 8 | 1 | 0 - video tutorials to implement 1v1 chat 3 - Firebase authentication | 3.5 |  |  | 4.5 |  |  |  |  | 3. Implementation of Firebase authentication for Google Login | 1. There was a issue (which got resolved) dealing with a presumed bug that user's could not log out. | 1. Bug resolved- use googleclient.signout() | 3. Presentation | 3
6 | 10/19-10/24 | 5 | 5 | 0 | 3. Write Iteration 1 Powerpoint |  |  |  | 5 |  |  |  |  | 3. Iteration 1 Powerppoint slides | 1. Team Communication could be improved |  | Regroup at team meeting to get more detailed tasking | NA (get update from team meeting- 10/26)
7 | 11/1-11/7 | 10 | 7 | 3 | 0. Learn how to use recyclerview for android 3. Implement user query by email | 4 |  |  | 3 | [5 empty] | 1. Team Communication could be improved |  | Push code to github and submit merge request | 12
8 | 11/8-11/14 | 7 | 6 | 1 | 3. Finalize code for user query; merge into Github |  |  |  | 6
9 | 11/15-11/21 | 10 | 8 | 2 | 0. Learning to connect queried chat to new chat message 3. Implement new chat mesage from query (client based code) | 6 |  |  | 4 |  |  |  |  | 3. Delivered branch that allows user to query and create chat message |  |  |  | 10
10 | 11/29-12/5 | 12 | 10 | 2 | 0. Learn Po's backend structure to link my previous week's code contribution (ie creating chat room) to a backend design 3. Implement retrieve chats from a backend code design 3. Create new chat room (ie create new chatroom from queried user) from a backend design | 7 |  |  | 3 |  |  |  |  | 3. Implementation of retrieving chats using backend desgin | 3. Could not fully complete creating new chatroom from a backend desing | Continue working on newchatroom (backend design) |  | 10
11 | 12/6-12/10 | 8 | 6 | 2 | 3. Create new chatroom 7. Documentation (testing) |  |  |  | 5 |  |  |  | 1 |  |  | 3. Created new chat room using Po's ChatRoomModel class, however. there were many code smells. After discussing, Po has already created new chatroom model at this point

## Jian Ma
Lead Roles: Backup Project Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/06-09/13 | 23 | 20 | 3 | 0 - learn git, read several tutorials 1 - research similar products, prepare presentation 2 - design product key features and target users 3 - set up git 5 - make project plan, send reminders to team members | 5 | 4 | 2 | 6 |  | 3 |  |  | 1. Write 3 sections of SPPP 2. Participate in Iteration 0 presentation 3. finish the application overview 4. paticipant meetings | 1. did not fegure out what is unique of our app 2. current features is a bit similar to other products 3. not familiar with git, many time-consuming bugs | 1. try to be more creative 2. Teach everyboard about git flow. 3. dig deeper for people's needs | 1 - work on user stories 2 - continue to learn git 3. -make features more specific | 12
2 | 09/13-09/20 | 16 | 13 | 3 | 1 - related product analysis 3 - complete readme.md with teammates 3 - prepare presentation 5 - make project plan, send reminders to team members | 7 |  | 4 |  |  | 2 |  |  | 1. analyze related product 2. feature out the target audience 3. Clear up SPPP 4. paticipant meetings | 1.Hard to find a suitable time for everyone 2. hard to understand every social app without using them all deeply | 1. postpone sleeping time 2. download apps and try 3. read marketing reports | 1. Start working on implementation | 16
4 | 09/27-10/04 | 12 | 9 | 3 | 0 - Learning firebase structure 0 - Learning framework of a chat application 3 - Add user stories at Pivot Tracker 5 - Team weekly meeting, scrum meeting | 5 |  |  | 3 |  | 1 |  |  | 1. add user stories on pIvotTracker | 1.feel like not on the same page with others | 1.more communication | 1. start working on user story document | 15
5 | 10/04 - 10/11 | 18 | 15 | 3 | 0 - Learning framework of a chat application 1 - Decide user stories for this iteration 2. - Draw the class diagram 2 - Learn user story graph and draw it | 5 | 2 | 8 | [5 empty] | 1. draw the class diagram 2. Decide user stories for this iteration | 1. don't know where to start the code | keeping learning | 1-work on user stories 2-continue to learn andorid and firebase | 20
3 | 09/20-09/27 | 13 | 10 | 3 | 0 - Learning Pivot Tracker 0 - Start learning Spring Boot. 1 - Planning tasks in Pivot Tracker 5 - Reschedule weekly, attend scrum meeting | 6 | 2 |  |  |  | 2 |  |  | -- | 1. too many stuff to learn | keep learning | keep learning | 15
6 | 10/11 - 10/18 | 24 | 21 | 3 | 0 - Learning template projects for both Android and Spring boot 0 - Learning sample project with firebase. 0 - Learning framework of a chat application 0 - Research key algorithms 2 - design presentation 3 - Prepare for the presentation 3 - Work on SDD document 5- Attend the Iteration meeting for iteration 1 | 9 |  | 2 | 8 |  | 2 |  |  | 1. Contribute in the slides, user stories, what we learn in this iteration 2. Wrap up the user stories document 3. Contribute in SDD, introduction, key algorithms, classes and methods. 4. Participate in the class presentation 5. have individual meetings with teammates to catch up | 1. communication is not enough | 1. enhance communication 2. change the way of collabarate 3. minimize work dependencies | working on the code | 30
7 | 10/18 - 10/25 | 6 | 6 | 0 | 1. Contribute in SDD, Data design 3. wrap up for Iteration 1 |  | 3 |  | 3 |  |  |  |  | 1. wrap up Iteration 1 3. Contribute in SDD, Data design |  |  | - explain what work has been done in the last interation | 7
8 | 10/25 - 11/1 | 10 | 7 | 3 | 0 - watch android studio tutorial 3 - try to fix network problems in emulator |  | 3 |  | 4 |  |  |  |  | 1. start iteration 2 |  |  |  | 8
9 | 11/1 - 11/8 | 14 | 12 | 2 | 1. Contribute in updating SDD, STD, 5. Had mini meeting with team mates. 3. fixed the emulator issue 3. Implement framework for profile photo |  | 3 |  | 7 |  | 2 |  |  | 1. Contribute in SDD, STD 2. coding for profile feature | lack of preparation for team management risks |  |  | 10
10 | 11/8 - 11/15 | 21 | 19 | 2 | 1. Contribute in updating SDD, STD, other reports 3 Implement framework for profile photo 7 prepare for the presentation 5 have meeting with team members |  | 3 |  | 8 |  | 3 |  | 5 | 1. implemente code and application deployment for Iteration 2 2. Contribute in SDD, Data Design and other documents 3. Prepare for the presentation | lack of preparation for team management risks | Coding!! |  | 17
11 | 11/15 - 11/22 | 10 | 8 | 2 | 0. Has small tutorial sessions for programming 3 - Firebase authentication 5. attend weekly meeting | 4 |  |  | 3 |  | 1 |  |  | 1. test the current project 2. Has some unit tests with TDD flow 3 Have clear owners of the tasks | Lack of communication between team member | have small meeting with teammates |  | 13
12 | 11/22 - 11/29 | 21 | 18 | 3 | 0. Has small tutorial sessions for UI, learn how to get pictures from network 2. design UI for profile picture 3. Start implementation of updating user's profile picture. 7. correct the mistakes in this document based on the professor's feedback | 5 |  | 3 | 8 |  |  |  | 2 | 1. delete previous improper branches 2. correct the mistakes in this document | lack of cooperation with teammates, pair programming would be useful | pair gramming with team more colabration Always be active and response |  | 15
13 | 11/29 - 12/06 | 25 | 20 | 5 | 0. Has small tutorial sessions for testing, TDD, backend structure 1. update user story document 3. comtinue implementation of updating user's profile picture. 5. discuss main responsiblity with team members 6. fix current android emulator bug | 5 | 3 |  | 5 |  | 3 | 4 |  | 1. update user story document 2. Fix all known issues 3. Has some unit tests on profile picture UI | bad time management, did not leave time for accidents | start early next week improve it by going to lecture |  | 20
14 | 12/06 - 12/10 | 30 | 25 | 5 | 0. Learning current backend structure and current code 1. requirement analysis for the previous iterations 1. draw user story diagram 2. design the presentation slides and make requirement analysis part 3. wrap up profile picture 3. commit the user profile UI to github 4. add test case for user profile on test document 4. test the released the version 5. discuss main responsiblity or owner of the tasks to team members 5. attend weekly meeting | 5 | 4 | 3 | 6 | 4 | 3 |  |  | 1. commit the view profile to github 2. Add user case diagram for the whole project 3. test several release versions 4. Contribute in all documents (SPPP, test doc, Code) 9. Contribute in presentation, and design the presentation | bad time management, optimistic about the tasks reflection on previous iterations. |  |  | 25

## Ananya
Lead Roles: Requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
2 | 09/13-09/20 | 6.7 | 5.2 | 1.5 | 0- Figure out the requirements of the project , 1 - Meeting with Professor for understanding the requirements , 2- Research on understnding the structure of mobile application , 3 - Work on iteration 0 presentation , 4- Lab 1 git work | 2 | 0.45 | 2 | 0.45 | 0.3 |  |  |  | 1. analyze related product 2. feature out the target audience 3. Learned Gitflow 4. paticipant meetings 5. Analyse Basic functionalities of the App | 1. Not familiar with gitflow 2. Difficult to fix a time for meeting | 1. Finish the presentation for iteration 0 | 0. Fifnish learning Gitflow,1. Learn basics of Firebase | 8
4 | 10/5 - 10/11 | 10 | 8 | 3 | 0- Define user stories and acceptance tests 1- Defining the requireements to the team better 2- Installed and configured Firebase | 2 | 3 | 4 |  |  |  | 0.5 |  | 1. User stories in Pivotaltracker | 1. Unsure about how will we implement firebase in the project
5 | 10/12 - 10/18 | 9 | 8 | 1 | 0- Learn about firebase and started familiarizing myself with the android studio. Android studio tutorials 1- Learned more about how NoSql works | 4 | 4 | [5 empty] | 0.5 | 1. Draw thw UML diagram 2. Decide user stories for iterartion 1 | 1. Still not clear how every component is going to come together |  |  | 60
6 | 10/19 - 10/25 | 10 | 9.5 | 2 | 0 - Android studio and Firebase tutorials 1 - Prepare Presentation | 7.5 | 2 | [6 empty] | 1. Helped make the slides for iteration 1 | 1. Not confident enough with android application design |  | 1. Review unit test content 2. Become familiar with current production code
7 | 10/25 - 11/1 | 8 | 7 | 3 | 0- Attend the Iteration meeting for iteration 2 1 - Work on Logo for the team 2 - Work on UI for the login page 3 - Learning android programming. | 1.5 | 1 | 2 | 2.5 |  |  |  |  | 1. Designed the logo for the app 2. Wrap up the user stories document 3. Participate in the class presentation 4. have individual meetings with teammates to catch up | 1. Not confident enough with android application design | 1. enhance communication 2. change the way of collabarate 3. minimize work dependencies | working on the code | 30
8 | 11/1 - 11/8 | 8 | 7 | 2 | 0- Attend the Iteration meeting for iteration 3 1 - Work on building unit tests 3 - Learning android unit testing methods. | 1.5 | 1.5 | 5 | [5 empty] | 1. Learned Junit and mockito to test android tests | 1. Not confident enough with android application design | 1. enhance communication 2. change the way of collabarate 3. minimize work dependencies
9 | 11/8 - 11/13 | 9 | 8 | 1 | 0- Attend the Iteration meeting for iteration 3 1 - Work on building unit tests 3 - Learning android unit testing methods. | [8 empty] | 1. Learned tutorials to test android tests | 1. Not confident enough with android application design and the integration with firebase | 1. enhance communication 2. change the way of collabarate 3. minimize work dependencies
10 | 11/15-11/21 | 7 | 5 | 2 | 0 - watch android studio tutorial 1 - try t set up emulator and Firebase | 4 | 3 | [6 empty] | 1. Learned tutorials to test android tests | 1. Understanding the testing techniques for android | 1. enhance communication 2. change the way of collabarate 3. minimize work dependencies
11 | 11/29-12/5 | 6 | 5 | 1 | 0 - watch android tutorial on building test code 1 - try to understand the backend code 2- write test code for backend code | 3 | 2 | 1 | [5 empty] | 1. Wrote the unit test for andriod code functions 2. have individual meetings with teammates to catch up | 1. Understanding the testing techniques for android | 1. enhance communication 2. change the way of collabarate 3. minimize work dependencies
12 | 12/6-12/10 | 10 | 8 | 2 | 0 - write test code on the backend code 1 - Learn different methods of building codes 2- Help make presenatation | 7 | 2 | 1 | [5 empty] | 1. Wrote the unit test for two andriod code functions 2. Work up the user stories document 3. have individual meetings with teammates to catch up | 1. Time management to deliver code | 1. enhance communication 2. change the way of collabarate 3. minimize work dependencies

## Raef
Lead Roles: Security Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
2 | 09/13-09/20 | 5.5 | 4.5 | 1 | 0 - learning encryption basics 1 - Define high level requirements | 3 | 1 | [5 empty] | 0.5 | Paricipate in presentation | 1- Lack of experince with the required skills 2- Tasks are not well defined 3- Action Items are ambiguous | 1-Examine comparable use cases 2- Voice concerns on action items in meeting | 1-Learn more about firebase 2-Learn more about TLS SSL 3-Try to develop an encryption tes.
3