## Summary-GroupIterationProgress
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks
0 | 09/06-09/20 | Learing git Git branching strategy - Git Flow Functional requirements Setup app foundation Risk identification Setup PivotalTracker Establish tech stacks Code style research Design Technology stacks for project |  | - Assigning documentation tasks | - Documentation responsibility - Team member awareness to the group's document | [5 empty] | 79.95 | 62.45 | 17.5 | 0 | 15.5 | 17.95 | 2 | 3.45 | 0.3 | 8
1
2
3

## projectcontribution
You should clearly describe your contribution to the group project in each category. (This is not the final iteration contribution. It is the whole semester contribution)
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Wasupol Tungsakultong | - Plan overall contents - Write process model - Write related work - Write implement and deployment plan | - creating one story on Pivotaltracker | - Planing tech stacks and architecture to use in the project. |  | - Plan overview of presentation - Outline presentation - Writing process model - Writing project timeline | - setup branches. - setup git structure. (Git flow) - setup branches rules'. - setup folder structure. |  |  | - Assigned roles and duties to team members - Assigned team plan and weekly meeting to the team
Jian Ma | - Set the tone for our product - Wrote the overall introduction - Wrote the competitive analysis |  | -Contributed features and design for our application |  | - Contributed overview of presentation - Writing overall introduction - Writing competitive analysis | - Contributed branches. - Contributed git structure. (Git flow) - setup files on git |  |  | - Had meetings with team member - Communicated daily by Slack

## Wasupol
Lead Roles: Project Leader, Configuration Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/06-09/13 | 8.5 | 5.5 | 3 | 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation |  | 2 |  |  |  | 2 | 0.5 | 1 | 1. Write 3 sections of SPPP 2. Participate in Iteration 0 presentation 3. Plan about process model, workflow to use in team project. | 1. communication is not clear. Task assignments is not clear. 2. very hard to setup meeting and communication because of mixture between online and in-person, also some team members live in difference time zone. | 1. Send task assignments to all members again. 2. Teach everyboard about git flow. | 1 - continue to define all requirements and start creating tasks 3 - setup android project in github. | 6
2 | 09/13-09/20 | 11 | 8 | 3 | 1 - define high level requirements, 1 - Design process model and timeline of the project 3 - Initialize android project on github 5 - make project plan, send reminders to team members 7 - prepare presentation |  | 3 |  | 1 |  | 2 |  | 2 | 1. Design project timeline for each iteration 2. Assign feature priorities 3. Clear up SPPP 4. Host meetings | 1. Not all members stay actively. | 1. Try to communicate more and direct | 1. Start working on implementation | 8
3 | 09/20-09/27

## Peter
Lead Roles: QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/13-09/20 | 5.75 | 4.75 | 1 | 0 - Learning basic git and watching pivot tracker tutorials 1 - Researching QA requirements for SPPP 3 - Lab 1 git work 7 - Software liscense look ups | 3 | 0.5 |  | 1 |  |  |  | 0.25 | 1. Set up git, commit to team introduction. 2. Looked up liscensing for QA/testing software: Junit, Selenium and Appium are all open sourced | 1. Ended up using git GUI rather than the console so I still need to spend more time familarizing myself with git. 2. Unsure of role in iteration 0 presentation & SPPP beyond basic statements concerning the QA Plan | 1. Discuss presentation and SPPP responsibilities on 9/20 | 1. Complete separate git tutorials using only the console 2. Contribute to SPPP | 6
2 | 09/20-09/27

## Michael
Lead Roles: Implementation Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/06-09/13 | 2 | 1 | 1 | 0 - learn git, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 1 | [7 empty] | 1. Set up git, commit a test message on git 2. Participate in Iteration 0 presentation | 1. Not to familiar with GitFlow | 1. Researching into kotlin resources for android development | 0 -learn GitFlow 1 - continue to define requirements | 3
2 | 09/13-09/20 | 2.5 | 1.5 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 1.5 | [7 empty] | 1. Write 3 sections of SPPP 2. Learned GitFlow 3. Configuration list Powerpoint | 1. Need to start ramping up learning out to work with Kotlin and Firebase | 1. Git Flow implementation | 0 -learn Kotlin 0 - learn to work with FireBase? | 2020-10-12
3

## Jian Ma
Lead Roles: Backup Project Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/06-09/13 | 23 | 20 | 3 | 0 - learn git, read several tutorials 1 - design product key features and target users 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 5 | 4 |  |  |  | 2 | 6 | 3 | 1. Write 3 sections of SPPP 2. Participate in Iteration 0 presentation 3. finish the application overview 4. paticipant meetings | 1. did not fegure out what is unique of our app 2. current features is a bit similar to other products 3. not familiar with git, many time-consuming bugs | 1. try to be more creative 2. Teach everyboard about git flow. 3. dig deeper for people's needs | 1 - work on user stories 2 - continue to learn git 3. -make features more specific | 12
2 | 09/13-09/20 | 15 | 12 | 3 | 1 - related product analysis 3 - complete readme.md with teammates 5 - make project plan, send reminders to team members 7 - prepare presentation |  | 7 |  | 1 |  | 2 |  | 2 | 1. analyze related product 2. feature out the target audience 3. Clear up SPPP 4. paticipant meetings | 1.Hard to find a suitable time for everyone 2. hard to understand every social app without using them all deeply | 1. postpone sleeping time 2. download apps and try 3. read marketing reports | 1. Start working on implementation | 16

## Ananya
Lead Roles: Requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
2 | 09/13-09/20 | 6.7 | 5.2 | 1.5 | 0- Figure out the requirements of the project , 1 - Meeting with Professor for understanding the requirements , 2- Research on understnding the structure of mobile application , 3 - Work on iteration 0 presentation , 4- Lab 1 git work | 2 | 0.45 | 2 | 0.45 | 0.3 |  |  |  | 1. analyze related product 2. feature out the target audience 3. Learned Gitflow 4. paticipant meetings 5. Analyse Basic functionalities of the App | 1. Not familiar with gitflow 2. Difficult to fix a time for meeting | 1. Finish the presentation for iteration 0 | 0. Fifnish learning Gitflow,1. Learn basics of Firebase | 8
3

## Raef
Lead Roles: Security Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
2 | 09/13-09/20 | 5.5 | 4.5 | 1 | 0 - learning encryption basics 1 - Define high level requirements | 3 | 1 | [5 empty] | 0.5 | Paricipate in presentation | 1- Lack of experince with the required skills 2- Tasks are not well defined 3- Action Items are ambiguous | 1-Examine comparable use cases 2- Voice concerns on action items in meeting | 1-Learn more about firebase 2-Learn more about TLS SSL 3-Try to develop an encryption tes.
3