## Sheet1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-10 with 1 lowest likelihood) | Estimated Impact (I:1-10 with 1 lowest impact) | Estimated retirement Cost (C: 1-10 with 1 lowest cost) | Priority (lowest number has high priority) (11-L)*(11-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personal | Loss team members | One or more team members drop the class; One or more team members may become ill and would be temporarily unavailable | 2 | 8 | 8 | 9*3*8=216 | team leader and all members | 2020-09-26 | Redefine the project scope if necessary, and assign the tasks to other team members. | Some people dropped class before it started; No one dropped the class after it strated | Open
| Lack of motivation or responsibility | One or more team members are not contributing to project due to lack of motivation | 2 | 3 | 5 | 9*8*5=360 | team leader and backup team leader | 2020-09-26 | Team leaders meet informally with team member to address the situation. Workload otherwise will transition to other team members |  | Open
Technology competence | Lack of familarity with framework | Individual team members are not familiar with the android framework, preventing them from initiating developlment of user stories | 5 | 6 | 4 | 5*6*4=120 | all members | 2020-10-22 | Assign appropiate tasks to those familiar with the framework, identify relevant tutorials for other members |  | Open
| Lack of familarity with programming languages | Individual team members are not familiar with Kotlin, Java | 7 | 2 | 2 | 7*2*2=28 | all members | 2020-10-22 | Kotlin interoperates with Java allowing team members to fallback on their experience with Java rather than being forced to use Kotlin |  | Open
Design and implementation | Significant Overhead moving from client based design to backend design | We had to significantly remodify our code so that we shift from a client centered code design to a design where the client code makes calls to the backend for creating&retrieving chatrooms | 8 | 7 | 2 | 112 | team leader and design/implementation members | 2020-12-01 | Create backend code design so that when client would like to open and retrieve a chatroom, the client code will call the backend to submit a request and correspondingly receive the response from a backend request. |  | Closed
Testing | Inadequete testing | Inadequete testing of releases due to lack of time and/or lack of familiarity with testing techniques | 7 | 5 | 5 | 7*5*5=175 | QA leader and all team members | 2020-10-22 | Release app as user stories are completed in order to facilitate testing |  | Open
Integration and deployment