## Summary-GroupIterationProgress
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks
0 | 09/06-09/20 | Learing git Git branching strategy - Git Flow Functional requirements Setup app foundation Risk identification Setup PivotalTracker Establish tech stacks Code style research Design Technology stacks for project |  | - Assigning documentation tasks | - Documentation responsibility - Team member awareness to the group's document | [5 empty] | 80.95 | 63.45 | 17.5 | 0 | 15.5 | 18.95 | 5 | 10.45 | 5.3 | 4
1 | 09/20-10/22 | Implementation Google API Login Setup all Firebase instances Requirement Analysis for Iteration 1 Scrum meeting - Weekly meeting Assign Tasks and Scrum Pokers Setup and config build tools and android distribution Setup appcenter Update PivotalTracker to Iterations | - Team's member have too much learning curve. | - personal issues among members | - start implementation of essential features | 5 | 12 | 0 | 0 | 0 | 171.5 | 139.5 | 32 | 0 | 31 | 26 | 15 | 38.5 | 3 | 14
2 | 10/22 - 11/13 | Implement Backend Code (Creating chatroom, send a message) Implement and setup for notifcation features Update UI and Application icon Setup Unit test and UI tests platform Update meeting schedules | - Team's member have too much learning curve. - All tech stacks are too new for team members | - member's health (flu) | - complete some features - refactor existing code - add unit tests | 5 | 12 | 0 | 0 | 0 | 160 | 130 | 30 | 0 | 32.5 | 21 | 13 | 37.5 | 3 | 15
3

## projectcontribution
You should clearly describe your contribution to the group project in each category. (This is not the final iteration contribution. It is the whole semester contribution)
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Wasupol Tungsakultong | - Plan overall contents - Write process model - Write related work - Write implement and deployment plan | - creating one story on Pivotaltracker | - Planing tech stacks and architecture to use in the project. - Add Design Pattern used - Add system architecture - Add detail implementation |  | - Plan overview of presentation - Outline presentation - Writing process model - Writing project timeline | - setup branches. - setup git structure. (Git flow) - setup branches rules'. - setup folder structure. |  | - set up automatic build tools (fastlane) - set up CI/CD (appcenter/circleci) | - Assigned roles and duties to team members - Assigned team plan and weekly meeting to the team
Jian Ma | - Set the tone for our product - Wrote the overall introduction - Wrote the competitive analysis |  | -Contributed features and design for our application |  | - Contributed overview of presentation - Writing overall introduction - Writing competitive analysis | - Contributed branches. - Contributed git structure. (Git flow) - setup files on git |  |  | - Had meetings with team member - Communicated daily by Slack
Peter Lake | - Wrote the quality assurance section | - Wrote several complete stories and contributed acceptance tests to others. | -Started class diagram for firebase implementation | -Summarized acceptance test results | - Wrote QA slide and created a chart to depict gitflow. | -Updated login UI with logo | -Manual testing of app log in/log out |  | -Meeting and communication via Slack -Contributed to risk management
Michael Ranasinghe |  | -Developed several user stories |  |  | - Contributed project management slide - Recorded video of querying users | -Contributed branch AddUserChatEmail - Contributed Google Login Branch |  |  | -Was accessible via Slack. I do best effort possible to be online slack ~16hr/day (just having it run in background with notifications on).

## Wasupol
Lead Roles: Project Leader, Configuration Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/06-09/13 | 8.5 | 5.5 | 3 | 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation |  | 2 |  |  |  | 2 | 0.5 | 1 | 1. Write 3 sections of SPPP 2. Participate in Iteration 0 presentation 3. Plan about process model, workflow to use in team project. | 1. communication is not clear. Task assignments is not clear. 2. very hard to setup meeting and communication because of mixture between online and in-person, also some team members live in difference time zone. | 1. Send task assignments to all members again. 2. Teach everyboard about git flow. | 1 - continue to define all requirements and start creating tasks 3 - setup android project in github. | 6
2 | 09/13-09/20 | 11 | 8 | 3 | 1 - define high level requirements, 1 - Design process model and timeline of the project 3 - Initialize android project on github 5 - make project plan, send reminders to team members 7 - prepare presentation |  | 3 |  | 1 |  | 2 |  | 2 | 1. Design project timeline for each iteration 2. Assign feature priorities 3. Clear up SPPP 4. Host meetings | 1. Not all members stay actively. | 1. Try to communicate more and direct | 1. Start working on implementation | 8
3 | 09/20-09/27 | 12 | 9 | 3 | 0 - Learning Pivot Tracker 1 - Planning tasks in Pivot Tracker 2 - Design Code and Document structure in github 3 - Add template code in github repository both backend and mobile code 5 - Reschedule weekly, start scrum meeting | 2 | 3 | 2 | 1 |  | 1 | [6 empty] | 10
4 | 09/27-10/04 | 12 | 9 | 3 | 1 - Update Readme.md 3 - update code structures 5 - Team weekly meeting, scrum meeting 6 - Setup gitflow branches |  | 2 |  | 2 |  | 3 | 2 | [5 empty] | 10
5 | 10/04 - 10/11 | 10 | 7 | 3 | 2 - Design folder structor of the project 3 - Setup template projects for both Android and Spring boot 3 - Setup Firebase project 6 - Configurate FCM message with the Android application |  | 2 | 3 |  |  |  | 2 |  | 1. Reviewing code 2. Setup Firebase instances 3. Fix defects of Google API login 4. Setup Firebase Firestore instance 5. Design data structure of Firebase Firestore. 6. Design chat mechanism for the application. | 1. team leader has personal issues so he can not 100% working on project. |  |  | 12
6 | 10/11 - 10/18 | 15 | 12 | 3 | 1, 5 - Iteration meeting for iteration 1 2 - Design overall software architecture to use in the project 3 - Implementation and setup Android and Backend project 5 - Configurate Pivotal Tracker like point and iteration 6 - setup automatic tools for building (fastlane), app center setup |  | 2 | 2 | 3 |  | 3 | 2 |  | 1. Reviewing code 2. Fix defects of Google API login 3. Implement fetch new messages listener 4. Implement the lifecycle of the application in each tab bar. 5. Setup distribution appCenter. |  |  |  | 15
7 | 10/18 - 10/25 | 13 | 13 | 0 | 1. Contribute in SDD, Data design, Design Patterns and System Architecture 3. Finalize code and application source code for Iteration 1, Fix defects in application source code 5. Plan for the next Iteration like tutorial and some demo for team member |  | 3 |  | 5 |  | 5 |  |  | 1. Finalize code and application source code for Iteration 1 2. Plan for the next Iteration like tutorial and some demo for team member 3. Contribute in SDD, Data design, Design Patterns and System Architecture 4. Fix defects in application source code |  |  | - start member trainning with Android development - explain what work has been done in the last interation - start restructure the code with backend - start integrate with backend | 18
8 | 10/25 - 11/1 | 11 | 8 | 3 | 3 - Start implement backend 5 - preparing demo, what was achieved in the last iteration in the term of implementation |  |  |  | 3 |  | 5 |  |  | 1. Design RestAPI endpoint and request that simply for client 2. setup code tutorial for team member 3. Start developing Backend with Java Spring boot |  |  |  | 15
9 | 11/1 - 11/8 | 8 | 6 | 2 | 1. Contribute in updating SDD, Data design, Design Pattern and System Architecture 3 Implement create a chatroom from Backend and save in firestore |  |  |  | 6 |  |  |  |  | 1. Contribute in SDD, Data Design and updated System Architecture 2. Fix defects in application 3. Start implementing code and core logics in backend 4. Setup FCM environment 5. Setup and add documents for setting up Android project for team member. | Lack of communication between team member |  |  | 15
10 | 11/8 - 11/13 | 13 | 11 | 2 | 1. Contribute in updating SDD, Data design, Design Pattern and System Architecture 3 Implement send a message from Backend and save in firestore 3 Implement send notification from backend to Firebase Cloud Message |  | 3 |  | 8 |  |  |  |  | 1. Finalize code and application deployment for Iteration 2 2. Plan for next iteration 3. Contribute in SDD, Data Design and updated System Architecture 4. Fix defects in application | Lack of communication between team member | Host 2 weekly meeting (shorter time like 30 mins) Always be active and response |  | 14

## Peter
Lead Roles: QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/13-09/20 | 5.75 | 4.75 | 1 | 0 - Learning basic git and watching pivot tracker tutorials 1 - Researching QA requirements for SPPP 3 - Lab 1 git work 7 - Software liscense look ups | 3 | 0.5 |  | 1 |  |  |  | 0.25 | 1. Set up git, commit to team introduction. 2. Looked up liscensing for QA/testing software: Junit, Selenium and Appium are all open sourced | 1. Ended up using git GUI rather than the console so I still need to spend more time familarizing myself with git. 2. Unsure of role in iteration 0 presentation & SPPP beyond basic statements concerning the QA Plan | 1. Discuss presentation and SPPP responsibilities on 9/20 | 1. Complete separate git tutorials using only the console 2. Contribute to SPPP | 6
2 | 09/20-09/27 | 8 | 6 | 2 | 0 - Read about types of QA tests and testing methods 7 - Prepare presentation, made gitflow defect management and prioritization flow chart, contribute to SPPP | 2 | [6 empty] | 4 | 1. QA section of SPPP 2. QA slide for presentation | 1. I need to learn about testing requirements and designing tests 2. It is difficult to write the task associated with user stories without having an undertanding of how chat software works. | 1. Discuss requirement analysis with group and review class materials about requirement analysis. | 1. Complete Lab 2 work 2. Complete risk analysis survey | 12
3 | 09/28-10/4 | 5 | 5 | 0 | 0- Learning about Pivotaltracker, EBC & UML class diagrams 1- Wrote user stories for lab 2 and class diagram | 3 | 2 | [6 empty] | 1. User stories in Pivotaltracker |  |  |  | 19
4 | 10/5 - 10/11 | 6.5 | 3.5 | 3 | 0- Read about using firebase to store user information 1- Additional user story creation and refinement 6- Installed and configured Android studio & IntelliJ | 1 | 2 |  |  |  |  | 0.5 |  | 1. User stories in Pivotaltracker | 1. Unsure of intended functionality of user feeds while writing user storied; we'll need to discuss this in a future iteration. 2. I'm worried about technical debt from me: firebase and regression testing. |  |  | 25
5 | 10/12 - 10/18 | 6.5 | 5.5 | 1 | 0- Continued to learn about firebase and started familiarizing myself with the android framework. Android studio tutorials 2- Started class diagram for backend firebase implementation since it will be needed to support initial user stories 7- Added information to risk management spreadsheet | 4 |  | 1 |  |  |  |  | 0.5 | 1. Risk management document 2. Backend class diagram |  |  |  | 30
6 | 10/19 - 10/25 | 5 | 4 | 1 | 0 - Android studio tutorials and starter project practise. Kotlin practise. Reading course notes related to testing. | 4 | [8 empty] | 1. Not compenent enough with android to start user stories from scratch. 2. There hasn't been time to begin any testing beyond manual testing by Po and Michael |  | 1. Review unit test content 2. Become familiar with current production code | 40
7 | 10/26 - 11/1 | 4 | 2 | 2 | 6- Spent time attempting to configure Android Studio in order to perform manual testing of login | [6 empty] | 2 | [5 empty] | 45
8 | 11/2 - 11/8 | 6 | 5 | 1 | 0 - Continued Android tutorials and worked with a starter project 6 - Resolved issues with Android/Firebase configuration that prevented google authentication | 4 | [5 empty] | 1 | [5 empty] | 50
9 | 11/9 - 11/15 | 15 | 13 | 2 | 0 - Researching techniques and configurations for unit & UI testing 3 - Created logo and added it to app login page 4 - Worked on unit test for google login, wrote up test reports for login page acceptance tests. 6 - Configured appium | 4 |  |  | 2 | 4 |  | 3 |  | 1. Software testing document 2. Unit tests for Lab 3 3. Updated log in UI with logo, marked user story as complete. | 1. Had difficulty configuring Appium/implementing UI test. 2. Unsure of how to write unit tests for the types of methods in the log in UI. Some of the assert statements that seem appropiate are failing to import. |  |  | 55

## Michael
Lead Roles: Implementation Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/06-09/13 | 2 | 1 | 1 | 0 - learn git, read several tutorials 5 - team meeting | 1 | [7 empty] | 0. Set up git, commit a test message on git 5. Participate in Iteration 0 presentation | 0. Not to familiar with GitFlow | 0. Researching into GitFlow | 0 -learn GitFlow 1 - continue to define requirements | 3
2 | 09/13-09/20 | 3.5 | 2.5 | 1 | 0 - Learned GitFlow 1 - define high level requirements and prepare presentation 5- team meeting | 1.5 | 1 | [6 empty] | 0. Learned GitFlow 1. Write 3 sections of SPPP 3. Configuration list Powerpoint | 0. Need to start ramping up learning out to work with Kotlin and Firebase |  | 0 -learn Kotlin 0 - learn to work with FireBase? | 2020-10-12
3 | 09/27-10/04 | 8 | 5 | 3 | 0- Kotlin Bootcamp Learning 5- team meeting | 5 | [10 empty] | First Task from pivotal tracker: Google Login | 10
4 | 10/5-10/12 | 10 | 9 | 1 | 0 - video tutorials to implement google log in 3 - Implementation of Google Log In API | 5.5 |  |  | 3.5 |  |  |  |  | 0. Reading Kotlin manuals/ Watching Videos on Implementing Android with Firebase 3. Implementation of Google Log In API |  |  | 3. Add in Facebook API Login; ensure user information is recorded within Firebase | 6-10hrs
5 | 10/12-10/19 | 9 | 8 | 1 | 0 - video tutorials to implement 1v1 chat 3 - Firebase authentication | 3.5 |  |  | 4.5 |  |  |  |  | 3. Implementation of Firebase authentication for Google Login | 1. There was a issue (which got resolved) dealing with a presumed bug that user's could not log out. | 1. Bug resolved- use googleclient.signout() | 3. Presentation | 3
6 | 10/19-10/24 | 5 | 5 | 0 | 3. Write Iteration 1 Powerpoint |  |  |  | 5 |  |  |  |  | 3. Iteration 1 Powerppoint slides | 1. Team Communication could be improved |  | Regroup at team meeting to get more detailed tasking | NA (get update from team meeting- 10/26)
7 | 11/1-11/7 | 10 | 7 | 3 | 0. Learn how to use recyclerview for android 3. Implement user query by email | 4 |  |  | 3 | [5 empty] | 1. Team Communication could be improved |  | Push code to github and submit merge request | 12
8 | 11/8-11/14 | 7 | 6 | 1 | 3. Finalize code for user query; merge into Github |  |  |  | 6

## Jian Ma
Lead Roles: Backup Project Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/06-09/13 | 23 | 20 | 3 | 0 - learn git, read several tutorials 1 - design product key features and target users 2 - make project plan, send reminders to team members 3 - set up git 4 - research similar products, prepare presentation | 5 | 4 | 2 | 6 | 3 |  |  |  | 1. Write 3 sections of SPPP 2. Participate in Iteration 0 presentation 3. finish the application overview 4. paticipant meetings | 1. did not fegure out what is unique of our app 2. current features is a bit similar to other products 3. not familiar with git, many time-consuming bugs | 1. try to be more creative 2. Teach everyboard about git flow. 3. dig deeper for people's needs | 1 - work on user stories 2 - continue to learn git 3. -make features more specific | 12
2 | 09/13-09/20 | 15 | 12 | 3 | 0 - related product analysis 1 - complete readme.md with teammates 2 - make project plan, send reminders to team members 3 - prepare presentation | 7 | 1 | 2 | 2 |  |  |  |  | 1. analyze related product 2. feature out the target audience 3. Clear up SPPP 4. paticipant meetings | 1.Hard to find a suitable time for everyone 2. hard to understand every social app without using them all deeply | 1. postpone sleeping time 2. download apps and try 3. read marketing reports | 1. Start working on implementation | 16
4 | 09/27-10/04 | 16 | 13 | 3 | 0 - Add user stories at Pivot Tracker 1 - Learning firebase structure 2 - Team weekly meeting, scrum meeting 3 - Learning framework of a chat application | 3 | 4 | 1 | 5 |  |  |  |  | 1. add user stories on pIvotTracker | 1.feel like not on the same page with others | 1.more communication | 1. start working on user story document | 15
5 | 10/04 - 10/11 | 17 | 14 | 3 | 0. - Draw the class diagram 1 - Decide user stories for this iteration 2 - Learn user story graph and draw it 3 - Learning framework of a chat application | 3 | 2 | 4 | 5 |  |  |  |  | 1. draw the class diagram 2. Decide user stories for this iteration | 1. don't know where to start the code | keeping learning | 1-work on user stories 2-continue to learn andorid and firebase | 20
3 | 09/20-09/27 | 12 | 9 | 3 | 0 - Learning Pivot Tracker 1 - Planning tasks in Pivot Tracker 2 - Reschedule weekly, attend scrum meeting 3 - Start learning Spring Boot. | 2 | 2 | 1 | 4 |  |  |  |  | -- | 1. too many stuff to learn | keep learning | keep learning | 15
6 | 10/11 - 10/18 | 23 | 20 | 3 | 0- Attend the Iteration meeting for iteration 1 1 - Prepare for the presentation 2 - Research key algorithms 3 - Work on SDD document 4 - Learning template projects for both Android and Spring boot 5 - Learning sample project with firebase. 6 - Learning framework of a chat application | 1 | 3 | 4 | 4 | 3 | 2 | 3 |  | 1. Contribute in the slides, user stories, what we learn in this iteration 2. Wrap up the user stories document 3. Contribute in SDD, introduction, key algorithms, classes and methods. 4. Participate in the class presentation 5. have individual meetings with teammates to catch up | 1. communication is not enough | 1. enhance communication 2. change the way of collabarate 3. minimize work dependencies | working on the code | 30
7 | 10/18 - 10/25 | 6 | 6 | 0 | 1. Contribute in SDD, Data design 3. wrap up for Iteration 1 |  | 3 |  | 3 |  |  |  |  | 1. wrap up Iteration 1 3. Contribute in SDD, Data design |  |  | - explain what work has been done in the last interation | 7
8 | 10/25 - 11/1 | 10 | 7 | 3 | 0 - watch android studio tutorial 3 - try to fix network problems in emulator |  | 3 |  | 4 |  |  |  |  | 1. start iteration 2 |  |  |  | 8
9 | 11/1 - 11/8 | 14 | 12 | 2 | 1. Contribute in updating SDD, STD, 5. Had mini meeting with team mates. 3. fixed the emulator issue 3. Implement framework for profile photo |  | 3 |  | 7 |  | 2 |  |  | 1. Contribute in SDD, STD 2. coding for profile feature | lack of preparation for team management risks |  |  | 10
10 | 11/8 - 11/13 | 21 | 19 | 2 | 1. Contribute in updating SDD, STD, other reports 3 Implement framework for profile photo 7 prepare for the presentation 5 have meeting with team members |  | 3 |  | 8 |  | 3 |  | 5 | 1. implemente code and application deployment for Iteration 2 3. Contribute in SDD, Data Design and other documents 4. Prepare for the presentation | lack of preparation for team management risks | Coding!! |  | 17

## Ananya
Lead Roles: Requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
2 | 09/13-09/20 | 6.7 | 5.2 | 1.5 | 0- Figure out the requirements of the project , 1 - Meeting with Professor for understanding the requirements , 2- Research on understnding the structure of mobile application , 3 - Work on iteration 0 presentation , 4- Lab 1 git work | 2 | 0.45 | 2 | 0.45 | 0.3 |  |  |  | 1. analyze related product 2. feature out the target audience 3. Learned Gitflow 4. paticipant meetings 5. Analyse Basic functionalities of the App | 1. Not familiar with gitflow 2. Difficult to fix a time for meeting | 1. Finish the presentation for iteration 0 | 0. Fifnish learning Gitflow,1. Learn basics of Firebase | 8
4 | 10/5 - 10/11 | 10 | 8 | 3 | 0- Define user stories and acceptance tests 1- Defining the requireements to the team better 2- Installed and configured Firebase | 2 | 3 | 4 |  |  |  | 0.5 |  | 1. User stories in Pivotaltracker | 1. Unsure about how will we implement firebase in the project
5 | 10/12 - 10/18 | 9 | 8 | 1 | 0- Learn about firebase and started familiarizing myself with the android studio. Android studio tutorials 1- Learned more about how NoSql works | 4 | 4 | [5 empty] | 0.5 | 1. Draw thw UML diagram 2. Decide user stories for iterartion 1 | 1. Still not clear how every component is going to come together |  |  | 60
6 | 10/19 - 10/25 | 10 | 9.5 | 2 | 0 - Android studio and Firebase tutorials 1 - Prepare Presentation | 7.5 | 2 | [6 empty] | 1. Helped make the slides for iteration 1 | 1. Not confident enough with android application design |  | 1. Review unit test content 2. Become familiar with current production code
6 | 10/11 - now | 25 | 13 | 3 | 0- Attend the Iteration meeting for iteration 1 1 - Prepare for the presentation 2 - Work on Logo for the team 3 - Work on UI for the login page 4 - Learning android programming. | 3 | 3 | 4 | 5 | 10 |  |  |  | 1. Contribute in the slides, user stories, what we learn in this iteration 2. Wrap up the user stories document 3. Participate in the class presentation 4. have individual meetings with teammates to catch up | 1. Not confident enough with android application design | 1. enhance communication 2. change the way of collabarate 3. minimize work dependencies | working on the code | 30

## Raef
Lead Roles: Security Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
2 | 09/13-09/20 | 5.5 | 4.5 | 1 | 0 - learning encryption basics 1 - Define high level requirements | 3 | 1 | [5 empty] | 0.5 | Paricipate in presentation | 1- Lack of experince with the required skills 2- Tasks are not well defined 3- Action Items are ambiguous | 1-Examine comparable use cases 2- Voice concerns on action items in meeting | 1-Learn more about firebase 2-Learn more about TLS SSL 3-Try to develop an encryption tes.
3